## Sheet1
Project Name | Master Thesis
Project Start | 2025-09-22
Current Date | 2025-04-14
Weeks in progress | -23
 | time axis 2025-09-22 to 2026-07-06
Task | Start Date | End Date | Days | Progress | time axis 2025-09-22 to 2026-07-06
Asses the utility of NDVI temporal signature for landslide detection
Litterature review | 2025-09-22 | 2025-10-05 | 13 | 0%
Data acquisition and preprocessing | 2025-09-22 | 2025-10-05 | 13 | 0%
Decomposition of time-series | 2025-09-22 | 2025-10-05 | 13 | 0%
Application of clustering techniques | 2025-09-22 | 2025-10-20 | 28 | 0%
Determine how post-landslide recovery varies based on anthropogenic and natural drivers
Selection of case studies | 2025-10-06 | 2025-10-19 | 13 | 0%
NDVI time-series extraction | 2025-10-13 | 2025-10-26 | 13 | 0%
Analyze correlations between recovery rates and drivers | 2025-10-27 | 2025-12-20 | 54 | 0%
Compare recovery patterns across case studies. | 2025-10-27 | 2025-12-20 | 54 | 0%
Test whether edge-zone analysis improves classification accuracy for ambiguous pixels
Define zones (landslide, edge, non-landslide) using spatial buffers | 2025-09-22 | 2025-10-05 | 13 | 0%
Analyze decomposition patterns of edge-zone pixels vs. pure landslide/non-landslide pixels. | 2025-10-27 | 2025-12-20 | 54 | 0%
Evaluate impact of edge-zone analysis on reducing false positives in automated detection | 2025-10-27 | 2025-12-20 | 54 | 0%
Writing Thesis
Introduction | 2026-03-31 | 2026-04-20 | 20 | 0%
Litterature | 2025-09-22 | 2025-11-30 | 69 | 0%
Methodology | 2025-09-22 | 2025-11-30 | 69 | 0%
Results | 2025-11-30 | 2026-01-31 | 62 | 0%
Discussion | 2026-02-09 | 2026-03-22 | 41 | 0%
Conclussion | 2026-03-31 | 2026-04-20 | 20 | 0%
Lay-out & references | 2026-04-13 | 2026-04-26 | 13 | 0%
Preparation oral defense | 2026-06-01 | 2026-06-28 | 27 | 0%
Meetings & Deadlines
First presentation | ? | ?
Second presentation | ? | ?
Soft deadline | 2026-05-04 | 2026-05-04
Submitting thesis | 2026-06-01 | 2026-06-01